## Project Schedule
PROJECT SCHEDULE TEMPLATE
PROJECT NAME | PROJECT MANAGER | Virtual Assistant | Caner Saka
PROJECT DELIVERABLE |  | Working browser-based chatbot and final report PDF
SCOPE STATEMENT |  | Rule-based chatbot with optional local LLM fallback, Gradio web UI, basic persistence
START DATE | END DATE | OVERALL PROGRESS
2025-10-01 | 2025-12-07 | 53%
TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION (in days) | STATUS | COMMENTS
Define project scope | Caner Saka | 2025-10-01 | 2025-10-03 | 3 | Complete
Set up GitHub repository | Caner Saka | 2025-10-01 | 2025-10-04 | 4 | Complete
Research chatbot approaches, libraries, models | Caner Saka | 2025-10-02 | 2025-10-07 | 6 | Complete
Select final tools/libraries | Caner Saka | 2025-10-08 | 2025-10-10 | 3 | Complete
Build project skeleton (basic chatbot loop) | Caner Saka | 2025-10-09 | 2025-10-14 | 6 | Complete
Implement baseline chatbot (rule-based replies) | Caner Saka | 2025-10-15 | 2025-10-18 | 4 | Complete
Test various scenarios | Caner Saka | 2025-10-19 | 2025-10-21 | 3 | Complete
Reevaluate scope | Caner Saka | 2025-10-22 | 2025-10-25 | 4 | Complete
Continue testing | Caner Saka | 2025-10-26 | 2025-10-31 | 6 | Complete
Refine conversation flow | Caner Saka | 2025-11-01 | 2025-11-07 | 7 | Planned
Add personality / specific rules /persistance | Caner Saka | 2025-11-08 | 2025-11-14 | 7 | Not Started
Test with sample conversations | Caner Saka | 2025-11-15 | 2025-11-21 | 6 | Not Started
Test gguf fallback | Caner Saka | 2025-11-22 | 2025-11-30 | 3 | Not Started
Polish responses and reliability | Caner Saka | 2025-12-01 | 2025-12-04 | 4 | Not Started
Complete PDF report | Caner Saka | 2025-12-05 | 2025-12-06 | 2 | Not Started
Final project submission | Caner Saka | 2025-12-07 | 2025-12-07 | 1 | Not Started